## Task Tracker
Health Facility Locator — Project Task Tracker
Task ID | Milestone | Task Description | Assignee | Start Date | Due Date | Status | Priority | Notes
TASK-01 | M1: Setup | Initialize project structure & dependencies | Freelancer | 10-Mar-26 | 12-Mar-26 | ✅ Done | High
TASK-02 | M1: Setup | Configure Google Maps API key & .env | Freelancer | 10-Mar-26 | 12-Mar-26 | ✅ Done | High | API key from Google Cloud Console
TASK-03 | M1: Setup | Set up base React app with routing | Freelancer | 12-Mar-26 | 14-Mar-26 | 🔄 In Progress | High
TASK-04 | M2: Core Map | Implement Google Maps component | Freelancer | 14-Mar-26 | 17-Mar-26 | ⏳ Pending | High
TASK-05 | M2: Core Map | Implement user geolocation (GPS) | Freelancer | 14-Mar-26 | 17-Mar-26 | ⏳ Pending | High
TASK-06 | M2: Core Map | Fetch nearby facilities via Places API | Freelancer | 17-Mar-26 | 20-Mar-26 | ⏳ Pending | High
TASK-07 | M2: Core Map | Add custom map markers per facility type | Freelancer | 17-Mar-26 | 20-Mar-26 | ⏳ Pending | Medium
TASK-08 | M3: Filters | Build facility type filter UI | Freelancer | 20-Mar-26 | 22-Mar-26 | ⏳ Pending | High
TASK-09 | M3: Filters | Build service filter (immunization etc.) | Freelancer | 20-Mar-26 | 22-Mar-26 | ⏳ Pending | High
TASK-10 | M3: Filters | Implement search by location/address | Freelancer | 22-Mar-26 | 24-Mar-26 | ⏳ Pending | Medium
TASK-11 | M4: Detail View | Build facility detail card component | Freelancer | 24-Mar-26 | 26-Mar-26 | ⏳ Pending | High
TASK-12 | M4: Detail View | Add Get Directions button | Freelancer | 24-Mar-26 | 26-Mar-26 | ⏳ Pending | Medium
TASK-13 | M4: Detail View | Display ratings & reviews | Freelancer | 26-Mar-26 | 28-Mar-26 | ⏳ Pending | Low
TASK-14 | M5: UI | Mobile responsive layout | Freelancer | 28-Mar-26 | 30-Mar-26 | ⏳ Pending | High
TASK-15 | M5: UI | Loading states & error handling | Freelancer | 28-Mar-26 | 30-Mar-26 | ⏳ Pending | Medium
TASK-16 | M5: UI | Empty state design | Freelancer | 30-Mar-26 | 01-Apr-26 | ⏳ Pending | Low
TASK-17 | M6: Testing | Unit tests for filtering logic | Freelancer | 01-Apr-26 | 03-Apr-26 | ⏳ Pending | High
TASK-18 | M6: Testing | Integration test for Maps API | Freelancer | 01-Apr-26 | 03-Apr-26 | ⏳ Pending | High
TASK-19 | M6: Testing | Cross-browser testing | Freelancer | 03-Apr-26 | 05-Apr-26 | ⏳ Pending | Medium
TASK-20 | M6: Testing | Final code review & documentation | Freelancer | 05-Apr-26 | 07-Apr-26 | ⏳ Pending | High

## Budget Tracker
Health Facility Locator — Budget Tracker
Item | Description | Estimated Cost ($) | Actual Cost ($) | Variance ($) | Payment Status | Notes
Freelancer Fee | Full project development fee (Fiverr) | 350 | 0 |  | ⏳ Pending | 50% upfront, 50% on delivery
Google Maps API | Monthly API usage (Places API) | 50 | 0 |  | ⏳ Pending | Monitor usage to avoid overages
Domain & Hosting | Project hosting during development | 20 | 0 |  | ⏳ Pending
Testing Tools | Browser testing & QA tools | 15 | 0 |  | ⏳ Pending
Contingency | Buffer for revisions or overruns | 50 | 0 |  | ⏳ Pending | ~10% of total budget
TOTAL

## Milestone Timeline
Health Facility Locator — Milestone Timeline
Milestone | Description | Start Date | End Date | Status | Owner
M1: Setup & Config | Project structure, API keys, base app | 10-Mar-26 | 14-Mar-26 | ✅ Done | Freelancer
M2: Core Map Feature | Maps, geolocation, facility markers | 14-Mar-26 | 20-Mar-26 | 🔄 In Progress | Freelancer
M3: Filtering & Search | Type filter, service filter, search | 20-Mar-26 | 24-Mar-26 | ⏳ Pending | Freelancer
M4: Facility Detail View | Cards, directions, ratings | 24-Mar-26 | 28-Mar-26 | ⏳ Pending | Freelancer
M5: UI & Responsiveness | Mobile design, error states | 28-Mar-26 | 01-Apr-26 | ⏳ Pending | Freelancer
M6: Testing & Delivery | QA, code review, documentation | 01-Apr-26 | 07-Apr-26 | ⏳ Pending | Freelancer